## Dashboard
Truck Packer 3D — Clean Feature Tracker
Generated 2026-05-24 from repo feature audit + current TODO direction. Keep TP3D-MASTER-TODO-V3.md as history; use this workbook as the clean tracker.
Metric | Formula / Value | Rank | Phase | Action | Priority | Timing
Total features tracked | 103 | 1 | AUTO-PACK-A0C | Run full browser stress pass: units, import/export, staged collision, wheel wells/front bonus, manual edits, PDF smoke. | P0 | Now
Completed / Verified | 68 | 2 | UI-STABILIZATION-3B | Settings mobile/responsive polish from approved main.css-only plan. | P1 | Next available
Open / Planned / Partial | 28 | 3 | AUTO-PACK-A1A | Add solver fixtures and stack rule tests before scoring changes. | P0 | After A0C
Deferred | 7 | 4 | AUTO-PACK-A1B | Improve scoring and stacking quality based on fixture failures. | P0 | After A1A
P0/P1 active pressure | 75 | 5 | Units Display Fix | If A0C confirms preferences save but UI does not update, fix user-facing conversion display. | P0/P1 | Conditional
|  | 6 | Import/Export Hardening | Fix any A0C import/export bugs; protect orientation/folders/sensitive-data boundaries. | P1 | Conditional
Recommended focus: finish AUTO-PACK-A0C browser stress first, then A1 solver fixtures/scoring. Keep UI mobile polish separate and do not begin app.js modularization yet. |  | 7 | Payload Scale | Add capacity/current/remaining/excess/% panel. | P1 | After A1
|  | 8 | Weight View | Add heatmap toggle with min/max controls. | P1 | After Scale
|  | 9 | Multi-solution AutoPack | Add dynamic Solution N of M model and UI. | P1 | After A1
|  | 10 | M0 Planning | Plan app.js modularization after geometry/solver contracts are stable. | P2 | Later

## Phase Roadmap
Phase | Status | Priority | Next Action | Notes
P0 Billing & Access | Verified / mostly green | P0 | Keep stable; finish portal edge-case validation | Do not mix with UI/AutoPack work.
P0 Workspace Foundation | Mostly verified | P0 | Restore billing refresh and transfer billing policy sign-off | Core creation/switching/archiving mostly stable.
P1 Membership Lifecycle | Mostly complete | P1 | Removed-member two-tab sign-off; Admin remove-member live sign-off | Invite core stable.
UI Stabilization | In progress | P1 | Run Settings mobile/responsive polish; Resources visual polish | Do before broad inline CSS migration.
AUTO-PACK-A0/A0B | Implemented | P0 | Run A0C browser stress pass | Orientation lock contract protected.
AUTO-PACK-A1 | Next solver phase | P0 | Fixture tests + stack rules + scoring quality | Must precede multi-solution.
AUTO-PACK-A2 | Planned | P1 | Dynamic 1–5 solution model and navigation | After single-solution correctness.
Payload / Weight View | Planned | P1 | Scale panel then Weight View | After pack stats and solver trust.
PDF Parity | Planned | P1/P2 | Weight capacity header; grouped case summary; color chips | After Scale/payload.
Crew View / Share | Deferred | P2 | Read-only share route and checklist | After reliable layouts and export/reporting.
Server-backed Packs/Cases | Planned | P1/P2 | Supabase table/RLS/data sync design | After local base stable.
M0 app.js Modularization | Deferred | P2 | Extract geometry then solver module | Not before P0/UI/AutoPack base.

## Feature Inventory
Category | Feature | Status | Priority | Phase | Owner | Next Action | Notes
3D Editor | Interactive Three.js editor: orbit, pan, zoom | Implemented | P1 | Editor Core |  | Validate during A0C browser pass | Core editor surface exists.
3D Editor | Top / Side / Perspective views | Implemented | P2 | Editor Core |  | Smoke test in browser | Ortho views exist; front/rear still future for PDF.
3D Editor | Case selection and multi-select | Implemented | P1 | Editor Core |  | Stress test selection after AutoPack | Click, shift-click, Ctrl/Cmd+A.
3D Editor | Drag / translate cases | Implemented | P1 | Editor Core |  | Stress test collision and bounds | Manual movement exists; boundary behavior must be tested.
3D Editor | Copy / paste / duplicate / delete cases | Implemented | P1 | Editor Core |  | A0C browser test; keyboard may be headless-sensitive | A0B preserves orientation metadata.
3D Editor | Undo / Redo | Implemented | P1 | Editor Core |  | Stress test after rotate, delete, AutoPack | StateStore-backed.
3D Editor | Snapping system | Partial | P1 | Editor Core |  | A0C collision/snap browser test | A0B fixed missing geometry-property usage.
3D Editor | Gravity / resting simulation | Partial | P0 | AutoPack A1 |  | A1 tests for stacking and staged items | Existing findRestingY; scoring/stack enforcement still needs hardening.
3D Editor | Staging area outside truck | Needs Validation | P0 | AutoPack A0C |  | Validate staged item spacing and collision | User wants staged/unpacked items not overlapping.
3D Editor | CoG indicator | Implemented | P2 | Editor Core |  | Defer until solver stable | Existing cog-service.
3D Editor | Performance overlay | Implemented | P3 | Dev Tooling |  | Keep | P key overlay.
Case Library | Create / edit cases with dimensions, color, weight, manufacturer, category | Implemented | P1 | Case Library |  | Regression test after unit fixes | Core case UI exists.
Case Library | Case categories and colors | Implemented | P2 | Case Library |  | Keep | Manage categories exists.
Case Library | Case search and sorting | Implemented | P2 | Case Library |  | Keep | Search, sort indicators.
Case Library | Cylinder / drum shape support | Implemented | P3 | Case Library |  | Validate volume sorting later | Geometry factory exists; volume calculation still tracked as possible low bug.
Case Library | Stackable true/false | Partial | P0 | AutoPack A1 |  | Enforce in solver with tests | Model has fields; enforcement still needs proof.
Case Library | noStackOnTop | Partial | P0 | AutoPack A1 |  | Add fixture and browser stress | A1 focus.
Case Library | Max stack count | Partial | P0 | AutoPack A1 |  | Clarify total tower enforcement | Currently partially enforced directly above base only.
Case Library | Manual orientation lock after rotate/flip | Implemented | P0 | AutoPack A0/A0B |  | A0C browser stress | A0 + A0B committed; metadata preserved.
Case Library | With Like stacking | Planned | P1 | AutoPack A1/B |  | Verify reference behavior before schema/UI change | Reference app evidence mixed; do not rush.
Case Library | Pallet flag | Deferred | P3 | Future Packing Groups |  | Defer | Model field exists, not used.
Case Library | Case Browser Category tab | Implemented | P2 | Editor Case Browser |  | Keep | Exists.
Case Library | Case Browser Manufacturer tab | Implemented | P2 | Editor Case Browser |  | Validate in browser | Codex says exists in current code.
Pack Management | Create / edit packs | Implemented | P1 | Pack Management |  | Keep | Title/client/project/truck dims.
Pack Management | Truck shape: rectangle | Implemented | P0 | Geometry |  | A0C validate | Standard container.
Pack Management | Truck shape: wheel wells | Implemented | P0 | Geometry |  | A0C validate no blocked-volume placement | Existing multi-zone geometry.
Pack Management | Truck shape: front bonus | Implemented | P0 | Geometry |  | A0C validate tall/short zones | Existing split zones.
Pack Management | Loading direction / unload order support | Planned | P1 | AutoPack A1/B |  | Add metadata after solver correctness | Needed for drop-off-first planning; not yet modelled.
Pack Management | Pack list/grid, search, filters, sorting | Implemented | P2 | Pack Management |  | Keep | Packs screen stable.
Pack Management | Pack statistics | Implemented | P1 | Pack Stats |  | Validate units and weight display | Volume %, weight totals, packed count, CoG.
Folder System | Folder dropdown and filter | Implemented | P2 | Phase 0.7C |  | Keep | Merged and validated.
Folder System | Create folder | Implemented | P2 | Phase 0.7C |  | Keep | Modal flow.
Folder System | Move pack to folder | Implemented | P2 | Phase 0.7C |  | Keep | Pack action menu.
Folder System | Rename/delete folder | Implemented | P2 | Phase 0.7C |  | Keep | Unfiled/all protected.
Folder System | Folder persistence on reload | Implemented | P1 | Phase 0.7C |  | Keep | Storage.saveNow flush.
Folder System | folderLibrary included in exports | Implemented | P1 | Import/Export |  | A0C export validation | Included in App and Workspace exports.
AutoPack | Single-solution AutoPack engine | Implemented | P0 | AutoPack Current |  | Improve quality before multi-solution | Greedy scanner exists.
AutoPack | Orientation lock respected by AutoPack | Implemented | P0 | AUTO-PACK-A0 |  | A0C stress pass | Commit e3212a7.
AutoPack | Orientation lock preserved across flows | Implemented | P0 | AUTO-PACK-A0B |  | A0C stress pass | Commit c5683b4.
AutoPack | Browser edge hardening for orientation lock | Implemented | P0 | AUTO-PACK-A0C-pre |  | Included in A0C follow-up | Commit bd4fdd0.
AutoPack | Full browser stress pass | Next | P0 | AUTO-PACK-A0C |  | Run broad browser stress prompt | Units/import/export/staged collision/manual edit.
AutoPack | Stack/no-stack/max stack fixture tests | Open | P0 | AUTO-PACK-A1A |  | Add fixture tests before scoring changes | Correctness foundation.
AutoPack | Stacking-aware scoring quality | Open | P0 | AUTO-PACK-A1B |  | Tune scoring after fixtures | Reduce valid staged leftovers.
AutoPack | Dynamic multi-solution model | Planned | P1 | AUTO-PACK-A2 |  | Only after single-solution quality | Support 1–5 solutions, not hard-code 5.
AutoPack | Delivery/unload order metadata | Planned | P1 | AUTO-PACK-A1/B |  | Add after A1 fixtures or with A2 strategy model | Needed for drop-off-first logic.
AutoPack | Weight-aware / heavy-low strategy | Planned | P1 | AUTO-PACK-A2 |  | After Scale/Weight stats trust | Strategy variant.
Import/Export | Export App Backup | Implemented | P1 | UI-COPY-EXPORT-IMPORT-1 |  | A0C export validation | Local packs/cases/folders/preferences.
Import/Export | Import App Backup | Implemented | P1 | UI-COPY-EXPORT-IMPORT-1 |  | A0C import validation | Replaces local app data.
Import/Export | Workspace Export | Implemented | P1 | Phase 0.7A |  | A0C workspace export validation | Owner/Admin, excludes sensitive data.
Import/Export | Workspace Import UI | Deferred | P2 | Future Import |  | Do not wire until product rules clear | Parser exists.
Import/Export | Export Pack JSON | Implemented | P1 | Import/Export |  | A0C pack export/import validation | One pack + cases.
Import/Export | Import Pack JSON | Implemented | P1 | Import/Export |  | A0C validation | Additive.
Import/Export | Cases CSV/XLSX import | Implemented | P1 | Import/Export |  | A0C validation | Adds valid rows, skips invalid/duplicates.
Import/Export | Download Cases Template | Implemented | P2 | Import/Export |  | Keep | CSV template.
Import/Export | PDF export | Implemented | P1 | Reporting |  | A0C smoke; later parity fixes | Codex says perspective/top/side/checklist/page nums already exist.
Import/Export | PDF weight capacity header | Planned | P1 | PDF Parity |  | After Scale/Payload model | Tracked gap.
Import/Export | PDF grouped case summary/color chips/front view | Planned | P2 | PDF Parity |  | After solver/Scale | Improve report quality.
Auth/Session | Supabase Auth signup/signin | Implemented | P0 | P0 Auth |  | Keep | Stable.
Auth/Session | Auto-org creation on signup | Verified | P0 | P0.10 |  | Keep | Test5 signup verified.
Auth/Session | Auth snapshot fallback | Verified | P0 | P0.7.2 |  | Keep | 8s TTL.
Auth/Session | Cross-tab sign-out | Verified | P0 | P0.9 |  | Keep | Validated.
Auth/Session | Separate-profile logout | Verified | P0 | P0 Release Gate |  | Keep | Validated.
Auth/Session | User-scoped local storage | Verified | P0 | P0.9 |  | Optional org-scoped future | Prevents cross-user leaks.
Workspace | Create workspace | Verified | P0 | Workspace Foundation |  | Keep | Modal flow.
Workspace | Switch workspace without billing/member/pack leakage | Verified | P0 | Workspace Foundation |  | Cases view sign-off optional | Browser proof exists.
Workspace | Archive workspace | Verified | P0 | Workspace Lifecycle |  | Keep | Owner-only, no Stripe mutation.
Workspace | Restore workspace | Needs Validation | P0 | Workspace Lifecycle |  | Live billing refresh sign-off | Implemented; sign-off open.
Workspace | Transfer ownership | Needs Validation | P0 | Workspace Lifecycle |  | Define/test billing ownership behavior | Implemented; billing policy open.
Workspace | Leave workspace | Verified | P0 | Workspace Lifecycle |  | Keep | Non-owner only; billing unchanged.
Workspace | Permanent delete workspace | Deferred | P2 | Workspace Lifecycle |  | Defer | Needs retention/export/ownership rules.
Workspace | Workspace slug / share-link model | Deferred | P2 | Phase S0 |  | Do not implement yet | Recommended secure pack share token.
Membership | Owner/Admin/Member roles | Implemented | P0 | Membership |  | Keep | Role model stable.
Membership | Invite create/resend/copy/accept | Verified | P1 | Membership |  | Keep | Staging validated.
Membership | Invite expiration/revocation | Verified | P1 | Membership |  | Keep | Server enforced.
Membership | Admin restrictions | Implemented | P0 | Role Hardening |  | Live Admin remove-member sign-off still open | RLS + Edge guard.
Membership | Removed-member access loss | Needs Validation | P1 | Membership |  | Two-tab live sign-off | Code implemented.
Billing | Owner-only billing UI/actions | Verified | P0 | Billing |  | Keep | Owner money actions.
Billing | Trial relative display | Verified | P0 | Billing |  | Keep | Ends in X days.
Billing | Trial-expired soft lock | Verified | P0 | Billing |  | Add screenshots/timestamps if needed | Sticky latch.
Billing | Past-due grace window | Implemented | P0 | Billing |  | Live edge-case sign-off if needed | Warning + block after grace.
Billing | Portal Manage fallback | Needs Validation | P0 | Billing |  | Verify stale/schedule-managed portal sessions | Code complete.
Billing | Billing retry reliability | Verified | P0 | Billing |  | Keep | Retry/refresh and failed-state poisoning fixed.
Billing | Workspace limit reached UI/gates | Verified | P0 | Billing |  | Keep | Real fixture exists.
Account Deletion | Delete account last-owner block | Implemented | P0 | Account Safety |  | Browser validation if not done | Server block message.
Account Deletion | 30-day deletion request | Implemented | P0 | Account Safety |  | Keep | Request state.
Account Deletion | Cancel deletion support endpoint | Implemented | P0 | Account Safety |  | Keep | Support-secret protected.
Account Deletion | Purge deleted accounts | Implemented | P0 | Account Safety |  | Manual/scheduler policy open | Support-invoked MVP.
Account Deletion | Self-service cancel deletion | Deferred | P2 | Account Safety |  | Defer | Requires token/session model.
UI/Theme | Light/dark theme | Implemented | P2 | UI |  | Keep | Theme toggle.
UI/Theme | Settings UI desktop stabilization | Implemented | P1 | UI-STABILIZATION-1/2 |  | Proceed to mobile polish | Advanced layout improved.
UI/Theme | Settings mobile/responsive polish | Next | P1 | UI-STABILIZATION-3B |  | Run responsive prompt | Main.css only planned.
UI/Theme | Resources tab visual consistency | Open | P2 | UI Stabilization |  | Polish after mobile or together if low risk | User still saw differences.
UI/Theme | Inline CSS migration | Open | P2 | UI Cleanup |  | After mobile and AutoPack A0C | Do not start now.
Security/Data | RLS and guardrails | Verified | P0 | Security |  | Keep | No wildcard CORS etc.
Security/Data | Sanitized JSON imports | Implemented | P0 | Import Safety |  | A0C import stress | Prototype pollution prevention.
Security/Data | DB health checks | Verified | P0 | P0.6 |  | Run before release | Q1-Q6 clean.
Future | Scale / Payload panel | Planned | P1 | Payload/Weight |  | After AutoPack A1 | Current/capacity/remaining/excess/%
Future | Weight View heatmap | Planned | P1 | Payload/Weight |  | After Scale | Visual only first.
Future | Crew View / read-only share link | Planned | P2 | Crew View |  | After solver/PDF | Large feature.
Future | Server-backed Packs/Cases | Planned | P1/P2 | Server Data |  | After P0 and AutoPack base | For collaboration and cross-device sync.
Future | app.js modularization | Deferred | P2 | M0 |  | After UI and AutoPack base | Do not start before contracts stable.
Future | Multi-container workflow | Planned | P3 | Expansion |  | Later | Across truck/container units.
Future | Enterprise API access | Deferred | P3 | Enterprise |  | Later | API keys, rate limits, SDK.

## Completed
Category | Feature | Status | Priority | Phase | Owner | Next Action | Notes
3D Editor | Interactive Three.js editor: orbit, pan, zoom | Implemented | P1 | Editor Core |  | Validate during A0C browser pass | Core editor surface exists.
3D Editor | Top / Side / Perspective views | Implemented | P2 | Editor Core |  | Smoke test in browser | Ortho views exist; front/rear still future for PDF.
3D Editor | Case selection and multi-select | Implemented | P1 | Editor Core |  | Stress test selection after AutoPack | Click, shift-click, Ctrl/Cmd+A.
3D Editor | Drag / translate cases | Implemented | P1 | Editor Core |  | Stress test collision and bounds | Manual movement exists; boundary behavior must be tested.
3D Editor | Copy / paste / duplicate / delete cases | Implemented | P1 | Editor Core |  | A0C browser test; keyboard may be headless-sensitive | A0B preserves orientation metadata.
3D Editor | Undo / Redo | Implemented | P1 | Editor Core |  | Stress test after rotate, delete, AutoPack | StateStore-backed.
3D Editor | CoG indicator | Implemented | P2 | Editor Core |  | Defer until solver stable | Existing cog-service.
3D Editor | Performance overlay | Implemented | P3 | Dev Tooling |  | Keep | P key overlay.
Case Library | Create / edit cases with dimensions, color, weight, manufacturer, category | Implemented | P1 | Case Library |  | Regression test after unit fixes | Core case UI exists.
Case Library | Case categories and colors | Implemented | P2 | Case Library |  | Keep | Manage categories exists.
Case Library | Case search and sorting | Implemented | P2 | Case Library |  | Keep | Search, sort indicators.
Case Library | Cylinder / drum shape support | Implemented | P3 | Case Library |  | Validate volume sorting later | Geometry factory exists; volume calculation still tracked as possible low bug.
Case Library | Manual orientation lock after rotate/flip | Implemented | P0 | AutoPack A0/A0B |  | A0C browser stress | A0 + A0B committed; metadata preserved.
Case Library | Case Browser Category tab | Implemented | P2 | Editor Case Browser |  | Keep | Exists.
Case Library | Case Browser Manufacturer tab | Implemented | P2 | Editor Case Browser |  | Validate in browser | Codex says exists in current code.
Pack Management | Create / edit packs | Implemented | P1 | Pack Management |  | Keep | Title/client/project/truck dims.
Pack Management | Truck shape: rectangle | Implemented | P0 | Geometry |  | A0C validate | Standard container.
Pack Management | Truck shape: wheel wells | Implemented | P0 | Geometry |  | A0C validate no blocked-volume placement | Existing multi-zone geometry.
Pack Management | Truck shape: front bonus | Implemented | P0 | Geometry |  | A0C validate tall/short zones | Existing split zones.
Pack Management | Pack list/grid, search, filters, sorting | Implemented | P2 | Pack Management |  | Keep | Packs screen stable.
Pack Management | Pack statistics | Implemented | P1 | Pack Stats |  | Validate units and weight display | Volume %, weight totals, packed count, CoG.
Folder System | Folder dropdown and filter | Implemented | P2 | Phase 0.7C |  | Keep | Merged and validated.
Folder System | Create folder | Implemented | P2 | Phase 0.7C |  | Keep | Modal flow.
Folder System | Move pack to folder | Implemented | P2 | Phase 0.7C |  | Keep | Pack action menu.
Folder System | Rename/delete folder | Implemented | P2 | Phase 0.7C |  | Keep | Unfiled/all protected.
Folder System | Folder persistence on reload | Implemented | P1 | Phase 0.7C |  | Keep | Storage.saveNow flush.
Folder System | folderLibrary included in exports | Implemented | P1 | Import/Export |  | A0C export validation | Included in App and Workspace exports.
AutoPack | Single-solution AutoPack engine | Implemented | P0 | AutoPack Current |  | Improve quality before multi-solution | Greedy scanner exists.
AutoPack | Orientation lock respected by AutoPack | Implemented | P0 | AUTO-PACK-A0 |  | A0C stress pass | Commit e3212a7.
AutoPack | Orientation lock preserved across flows | Implemented | P0 | AUTO-PACK-A0B |  | A0C stress pass | Commit c5683b4.
AutoPack | Browser edge hardening for orientation lock | Implemented | P0 | AUTO-PACK-A0C-pre |  | Included in A0C follow-up | Commit bd4fdd0.
Import/Export | Export App Backup | Implemented | P1 | UI-COPY-EXPORT-IMPORT-1 |  | A0C export validation | Local packs/cases/folders/preferences.
Import/Export | Import App Backup | Implemented | P1 | UI-COPY-EXPORT-IMPORT-1 |  | A0C import validation | Replaces local app data.
Import/Export | Workspace Export | Implemented | P1 | Phase 0.7A |  | A0C workspace export validation | Owner/Admin, excludes sensitive data.
Import/Export | Export Pack JSON | Implemented | P1 | Import/Export |  | A0C pack export/import validation | One pack + cases.
Import/Export | Import Pack JSON | Implemented | P1 | Import/Export |  | A0C validation | Additive.
Import/Export | Cases CSV/XLSX import | Implemented | P1 | Import/Export |  | A0C validation | Adds valid rows, skips invalid/duplicates.
Import/Export | Download Cases Template | Implemented | P2 | Import/Export |  | Keep | CSV template.
Import/Export | PDF export | Implemented | P1 | Reporting |  | A0C smoke; later parity fixes | Codex says perspective/top/side/checklist/page nums already exist.
Auth/Session | Supabase Auth signup/signin | Implemented | P0 | P0 Auth |  | Keep | Stable.
Auth/Session | Auto-org creation on signup | Verified | P0 | P0.10 |  | Keep | Test5 signup verified.
Auth/Session | Auth snapshot fallback | Verified | P0 | P0.7.2 |  | Keep | 8s TTL.
Auth/Session | Cross-tab sign-out | Verified | P0 | P0.9 |  | Keep | Validated.
Auth/Session | Separate-profile logout | Verified | P0 | P0 Release Gate |  | Keep | Validated.
Auth/Session | User-scoped local storage | Verified | P0 | P0.9 |  | Optional org-scoped future | Prevents cross-user leaks.
Workspace | Create workspace | Verified | P0 | Workspace Foundation |  | Keep | Modal flow.
Workspace | Switch workspace without billing/member/pack leakage | Verified | P0 | Workspace Foundation |  | Cases view sign-off optional | Browser proof exists.
Workspace | Archive workspace | Verified | P0 | Workspace Lifecycle |  | Keep | Owner-only, no Stripe mutation.
Workspace | Leave workspace | Verified | P0 | Workspace Lifecycle |  | Keep | Non-owner only; billing unchanged.
Membership | Owner/Admin/Member roles | Implemented | P0 | Membership |  | Keep | Role model stable.
Membership | Invite create/resend/copy/accept | Verified | P1 | Membership |  | Keep | Staging validated.
Membership | Invite expiration/revocation | Verified | P1 | Membership |  | Keep | Server enforced.
Membership | Admin restrictions | Implemented | P0 | Role Hardening |  | Live Admin remove-member sign-off still open | RLS + Edge guard.
Billing | Owner-only billing UI/actions | Verified | P0 | Billing |  | Keep | Owner money actions.
Billing | Trial relative display | Verified | P0 | Billing |  | Keep | Ends in X days.
Billing | Trial-expired soft lock | Verified | P0 | Billing |  | Add screenshots/timestamps if needed | Sticky latch.
Billing | Past-due grace window | Implemented | P0 | Billing |  | Live edge-case sign-off if needed | Warning + block after grace.
Billing | Billing retry reliability | Verified | P0 | Billing |  | Keep | Retry/refresh and failed-state poisoning fixed.
Billing | Workspace limit reached UI/gates | Verified | P0 | Billing |  | Keep | Real fixture exists.
Account Deletion | Delete account last-owner block | Implemented | P0 | Account Safety |  | Browser validation if not done | Server block message.
Account Deletion | 30-day deletion request | Implemented | P0 | Account Safety |  | Keep | Request state.
Account Deletion | Cancel deletion support endpoint | Implemented | P0 | Account Safety |  | Keep | Support-secret protected.
Account Deletion | Purge deleted accounts | Implemented | P0 | Account Safety |  | Manual/scheduler policy open | Support-invoked MVP.
UI/Theme | Light/dark theme | Implemented | P2 | UI |  | Keep | Theme toggle.
UI/Theme | Settings UI desktop stabilization | Implemented | P1 | UI-STABILIZATION-1/2 |  | Proceed to mobile polish | Advanced layout improved.
Security/Data | RLS and guardrails | Verified | P0 | Security |  | Keep | No wildcard CORS etc.
Security/Data | Sanitized JSON imports | Implemented | P0 | Import Safety |  | A0C import stress | Prototype pollution prevention.
Security/Data | DB health checks | Verified | P0 | P0.6 |  | Run before release | Q1-Q6 clean.

## Open TODO
Category | Feature | Status | Priority | Phase | Owner | Next Action | Notes
3D Editor | Snapping system | Partial | P1 | Editor Core |  | A0C collision/snap browser test | A0B fixed missing geometry-property usage.
3D Editor | Gravity / resting simulation | Partial | P0 | AutoPack A1 |  | A1 tests for stacking and staged items | Existing findRestingY; scoring/stack enforcement still needs hardening.
3D Editor | Staging area outside truck | Needs Validation | P0 | AutoPack A0C |  | Validate staged item spacing and collision | User wants staged/unpacked items not overlapping.
Case Library | Stackable true/false | Partial | P0 | AutoPack A1 |  | Enforce in solver with tests | Model has fields; enforcement still needs proof.
Case Library | noStackOnTop | Partial | P0 | AutoPack A1 |  | Add fixture and browser stress | A1 focus.
Case Library | Max stack count | Partial | P0 | AutoPack A1 |  | Clarify total tower enforcement | Currently partially enforced directly above base only.
Case Library | With Like stacking | Planned | P1 | AutoPack A1/B |  | Verify reference behavior before schema/UI change | Reference app evidence mixed; do not rush.
Case Library | Pallet flag | Deferred | P3 | Future Packing Groups |  | Defer | Model field exists, not used.
Pack Management | Loading direction / unload order support | Planned | P1 | AutoPack A1/B |  | Add metadata after solver correctness | Needed for drop-off-first planning; not yet modelled.
AutoPack | Full browser stress pass | Next | P0 | AUTO-PACK-A0C |  | Run broad browser stress prompt | Units/import/export/staged collision/manual edit.
AutoPack | Stack/no-stack/max stack fixture tests | Open | P0 | AUTO-PACK-A1A |  | Add fixture tests before scoring changes | Correctness foundation.
AutoPack | Stacking-aware scoring quality | Open | P0 | AUTO-PACK-A1B |  | Tune scoring after fixtures | Reduce valid staged leftovers.
AutoPack | Dynamic multi-solution model | Planned | P1 | AUTO-PACK-A2 |  | Only after single-solution quality | Support 1–5 solutions, not hard-code 5.
AutoPack | Delivery/unload order metadata | Planned | P1 | AUTO-PACK-A1/B |  | Add after A1 fixtures or with A2 strategy model | Needed for drop-off-first logic.
AutoPack | Weight-aware / heavy-low strategy | Planned | P1 | AUTO-PACK-A2 |  | After Scale/Weight stats trust | Strategy variant.
Import/Export | Workspace Import UI | Deferred | P2 | Future Import |  | Do not wire until product rules clear | Parser exists.
Import/Export | PDF weight capacity header | Planned | P1 | PDF Parity |  | After Scale/Payload model | Tracked gap.
Import/Export | PDF grouped case summary/color chips/front view | Planned | P2 | PDF Parity |  | After solver/Scale | Improve report quality.
Workspace | Restore workspace | Needs Validation | P0 | Workspace Lifecycle |  | Live billing refresh sign-off | Implemented; sign-off open.
Workspace | Transfer ownership | Needs Validation | P0 | Workspace Lifecycle |  | Define/test billing ownership behavior | Implemented; billing policy open.
Workspace | Permanent delete workspace | Deferred | P2 | Workspace Lifecycle |  | Defer | Needs retention/export/ownership rules.
Workspace | Workspace slug / share-link model | Deferred | P2 | Phase S0 |  | Do not implement yet | Recommended secure pack share token.
Membership | Removed-member access loss | Needs Validation | P1 | Membership |  | Two-tab live sign-off | Code implemented.
Billing | Portal Manage fallback | Needs Validation | P0 | Billing |  | Verify stale/schedule-managed portal sessions | Code complete.
Account Deletion | Self-service cancel deletion | Deferred | P2 | Account Safety |  | Defer | Requires token/session model.
UI/Theme | Settings mobile/responsive polish | Next | P1 | UI-STABILIZATION-3B |  | Run responsive prompt | Main.css only planned.
UI/Theme | Resources tab visual consistency | Open | P2 | UI Stabilization |  | Polish after mobile or together if low risk | User still saw differences.
UI/Theme | Inline CSS migration | Open | P2 | UI Cleanup |  | After mobile and AutoPack A0C | Do not start now.
Future | Scale / Payload panel | Planned | P1 | Payload/Weight |  | After AutoPack A1 | Current/capacity/remaining/excess/%
Future | Weight View heatmap | Planned | P1 | Payload/Weight |  | After Scale | Visual only first.
Future | Crew View / read-only share link | Planned | P2 | Crew View |  | After solver/PDF | Large feature.
Future | Server-backed Packs/Cases | Planned | P1/P2 | Server Data |  | After P0 and AutoPack base | For collaboration and cross-device sync.
Future | app.js modularization | Deferred | P2 | M0 |  | After UI and AutoPack base | Do not start before contracts stable.
Future | Multi-container workflow | Planned | P3 | Expansion |  | Later | Across truck/container units.
Future | Enterprise API access | Deferred | P3 | Enterprise |  | Later | API keys, rate limits, SDK.

## AutoPack Plan
Phase | Status | Goal | Tests / Browser Checks | Do Not Touch | Output
A0C Browser Stress | Next | Find unit, import/export, staged item, collision, geometry, manual edit bugs. | Units save/reload, import/export, staged spacing, wheel wells, front bonus, manual rotate/flip, PDF smoke. | Billing/auth/Supabase/Stripe/CSS/multi-solution. | Fix confirmed bugs + report.
A1A Fixtures | Open | Add repeatable solver fixtures before quality changes. | noStackOnTop, stackable false, maxStackCount, locked orientation, wheel wells, front bonus, staged items. | UI polish/multi-solution. | Tests that fail for real bugs.
A1B Scoring | Open | Improve single-solution packing quality. | Support-area bonus, vertical fill, heavy-low, valid small cases not left staged. | Multi-solution UI. | Better packed count and fewer valid staged items.
A2 Multi-Solution | Planned | Dynamic 1–5 solution output. | Prev/next solution, apply solution, stats, unpacked list, rerun. | Server rewrite, Crew View. | Solution N of M model.
A3 Delivery Order | Planned | Support load/unload/drop-off sequence. | stopGroup, deliverySequence, mustUnloadFirst, mustLoadLast, keepTogetherGroup. | Reuse groupId incorrectly. | Strategy-aware solver inputs.
C1 Scale | Planned | Add payload capacity UI. | Capacity, current, remaining, excess, %, warning. | Use weight to block solver initially. | Trusted load accounting.
C2 Weight View | Planned | Add weight heatmap. | Min/max, live colors, labels visible. | Solver changes. | Visual-only overlay first.

## Risks Decisions
Risk / Decision | Priority | Status | Next Action
AutoPack staged/unpacked overlap | P0 | Open | A0C browser stress; fix staged placement spacing if confirmed.
Units preferences do not update UI | P0/P1 | Open | A0C browser test; fix display conversion if confirmed.
AutoPack stack quality leaves valid items staged | P0 | Open | A1 fixtures and scoring.
Duplicate geometry helpers can drift | P1 | Open | Extract one geometry source after A1 contracts.
Portal Manage fallback not fully manually verified | P0 | Needs Validation | Run stale/schedule-managed portal tests.
Restore workspace billing refresh | P0 | Needs Validation | Live test restore flow.
Transfer billing ownership policy | P0 | Needs Decision | Define and sign off.
Settings Resources inconsistent UI | P2 | Open | Polish after mobile or in small CSS pass.
Inline style debt | P2 | Open | Migrate after responsive and AutoPack A0C.
Server-backed packs/cases | P1/P2 | Needs Design | Decision on Supabase data model and migration.

## Legend
Field | Allowed Values / Meaning
Status | Implemented, Verified, Partial, Needs Validation, Open, Next, Planned, Deferred
Priority | P0 = release blocker/high risk, P1 = next product quality, P2 = important later, P3 = expansion
Phase | Use the major phase name: Billing, Workspace, AutoPack, UI, Import/Export, Future
Owner | Optional; assign person/AI when ready
Rule | TP3D-MASTER-TODO-V3.md remains history. This workbook is the cleaner tracker.